## ListOfFeatures
Product Backlog - Gym one (List of your features)
User Stories / List of features
User
buy a membership
contact us thorough a form on contact page
contact trainers directly
view:memberships, trainers,gallery images, slider, blog posts
admin:
can login(without login cannot change stuff)done
can add membership
can add trainers
can add gallery_images
can add slider
can add blog
update membership
update trainers
update gallery_image
update slider
update blog
delete membership
delete trainers
delete gallery_images
delete slider
delete blog

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS
User Story/ Feature #1
database design |  | whole team | done
listof features |  | whole team | done
login |  | deepan | done
header |  | danila | done
footer |  | kasmir | done
divider |  | danila | ongoing
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
membership crud |  | kasmir | testing
trainers crud |  | danila | ongoing
admin universal header footer |  | deepan | done
slider crud |  | deepan | done
contact.php |  | kasmir | done
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
fixing user stuff and links |  | kasmir | ongoing
fixing broken stuff and testing that it works |  | all | ongoing
trainer needs img |  | danila | ongoing
finalizing the project |  | all | ongoing
User Story #2
gallery |  | deepan | ongoing
blog |  | deepan | ongoing
displayinng stuff on frontend(user) |  | kasmir | ongoing
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.